|  | Matching Grants The Rotary Foundation Report to The Rotary Foundation One Rotary Center 1560 Sherman Ave. Evanston, IL 60201-3698, USA Fax: 847-556-2151 E-mail: contact.center@rotary.org |
| --- | --- |

The primary partner Rotary clubs/districts must submit Progress Reports every twelve months during project implementation.  The Final Report is due two months after completing the project.

Project Information

| Matching Grant Number | 73310 | Project Country | Guyana |
| --- | --- | --- | --- |

| X | Progress report |  | Final report | Reporting Period from: |  | to | 28/02/2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Host Partner Rotary Club: | Georgetown Rotary Club |  | District: |  |
| --- | --- | --- | --- | --- |
| International Partner Rotary Club: |  | Southborough Rotary Club | District: | 7910 |

Project Narrative

1. Briefly describe the project. - What were your original objectives?

This project is to improve the quality of pre-hospital emergency medicine in Guyana. This is a project, which is part of a ministry of health project to improve the quality of pre-hospital emergency medicine in Guyana. The Rotary part of this project is to teach a group of highly skilled nurses to have the knowledge and teaching skills to train the ambulance attendants who will be the first on the scene in an accident or health emergency situation. The objective is to leave a permanent knowledge base in the country.

- What was actually accomplished? (Photographs can help to tell your story. Please submit any action photos that you have that show beneficiary participation and demonstrate Rotarian involvement in the project. Please also indicate the name of the photographer.)

Over $20,000.00 of the Matching Grant has been spent to date. Purchased items include manuals for the students, mannequins, and training equipment. Materials were purchased in the United States and shipped to Guyana. The shipping expenses are paid with non-grant funds. We were able to arrange free ocean transport of our equipment and manuals from Miami to Georgetown. 25 nurses attended the class. The teachers were very impressed with the skill levels of the students. The morning sessions consisted of classroom instruction; the afternoons consisted of teaching stations. The stations used the mannequins and other training materials purchased with the matching grant.

- When and where did the project take place, and who were the beneficiaries?

The Georgetown Public Hospital arranged for the teaching to take place in the Dawn Training Center, which had teaching rooms, breakout rooms and other needed space. The immediate beneficiaries are the 25 students – 3 from Balwand Singh’s Hospital, 2 from Davis Memorial Hospital, 3 from St. Joseph’s Mercy Hospital, 1 from the Red Cross, 16 from the Georgetown Public Hospital. The intermediate beneficiaries will be the ambulance attendants, the ultimate beneficiaries will be the patients who are helped or saved by the teaching skills that are imparted to our students.

2. Scope change. If the project was changed, how and why was it changed?

The scope of the project has been unchanged.

Rotarian Involvement and Oversight

| 3. How did Rotarians manage and oversee the project? |  |
| --- | --- |
| The sponsor Rotarians raised funds from the clubs and District 7910. The Rotarians developed the teaching portion of the project in partnership, working with the Physicians and paramedics from the United States. The Georgetown Rotarians arranged liaison with the Guyana medical community, took care of the team in country, arranged transportation, lunches for the students and the team, and lodging for the team in country. They also arranged publicity events, press conference. |  |
| 4. How many Rotarians from the host partner club participated in the project? 9 Rotarians from Georgetown Rotary Club actively participated in the project. | 9 |
| 5. In what way did the host Rotarians participate in the project? Please list all non-financial involvement. |  |
| The host Rotarians arranged lodging, meals for students and team, hosted us at their Rotary meeting, visited the teaching site, arranged publicity and provided a social gathering for all involved persons and other members of the community. |  |
| 6. How many Rotarians from the international partner club participated in the project? This project was a partnership of 8 international partner clubs. | 8 |
| 7. In what way did the international Rotarians participate in the project? Please list all non-financial involvement. |  |
| The international Rotarians organized the project. We did preliminary studies with visits to Guyana and worked with the Ministry of Health and Georgetown Public Health Center (GPHC) to determine their needs. Based on their vision of their needs, we designed the project. We prepared a proposal and we designed the Matching Grant. We also organized the teaching team. We coordinated with the GPHC and the Georgetown Rotary Club to assure success. Further work with the Georgetown Public Health Center has involved Rotarians and our faculty. We are adjusting our programs as the project progresses. |  |

###### Community Impact

| 8. How many people benefited from the project? The immediate beneficiaries are the 25 nurses who attended the classes. | 25 |
| --- | --- |
| 9. What was the impact of the project on the beneficiaries? |  |
| The future teaching leaders in the class had their medical knowledge increased and their teaching skills were advanced. A Certificate of Accomplishment was awarded to each of the 25 participants. |  |
| 10. What are the expected long-term community impacts of the project? |  |
| These trained teachers of pre-hospital skills are the nucleus of a Ministry of Health program to build an improved ambulance system. We are aiding in the training of ambulance personnel by developing a permanent core of nurses trained to teach ambulance personnel. |  |

Financial Statement

| Currency Used: | USD | Exchange Rate: | 1 | = 1 USD |
| --- | --- | --- | --- | --- |

11.  Income

| Sources of Income |  | Currency | Amount |
| --- | --- | --- | --- |
| 1. TRF Matching Grant Award and Contributions |  | $39,656.00 |  |
| 2. Other Income (identify): |  |  |  |
| 3. Other Income (identify): | 7910 Rotary Clubs |  |  |
| 4. Interest Income (if any): |  |  |  |
| Total Income: |  | $39,656. |  |

12. Expenses (add rows as needed)

| Budget Items | # Name of supplier | Currency | Amount |
| --- | --- | --- | --- |
| 1. Laptops | Office Max | $1,150.00 |  |
| 2. Flashdrives | Amazon | $360.00 |  |
| 3. Supplies & Equipment | Boundtree | $12,309.00 |  |
| 4. Software | Academic Superstore | $256.00 |  |
| 5. Projector | Amazon | $336.00 |  |
| 6. Labels | Curry Printing | $210.00 |  |
| 7. Books | Atlantic Partners | $2,502.00 |  |
| 8. |  |  |  |
|  | Total Expenses: | $17,123.00 |  |

13. Bank Statement - A bank statement that supports the above statement of income and expenses must be attached to this report.

Important – please read:

- For final reports, if there is less than US$200 remaining, please spend it on eligible items.

If there is more than US$200 remaining, it must be returned to The Rotary Foundation.

[Note: In India, government rules require that all unutilized funds be returned to the Rotary International South Asia Office.]

- For grant awards over US$25,000, attach an Independent Financial Review to each progress report and the final report.

- Keep all original receipts for at least five years, or longer if required by local law.  Do not send receipts to TRF unless requested by staff.

- If your project involves a revolving loan fund you will need to visit the Rotary website at: ‘www.rotary.org’ to download the Report Supplement for Revolving Loan Grants.

14. Certifying Signature – Either the Host or International Partner must certify the report. If the grant is club sponsored the current club president must certify the report and if the grant is district-sponsored the district grants subcommittee chair must certify the report.

By signing this report, I confirm to the best of my knowledge that these Matching Grant funds were spent according to Trustee-approved guidelines and that all of the information contained herein is true and accurate.  Original receipts for all expenses incurred will be kept on file for at least five years, or longer if required by local law, in case they are needed for auditing purposes. I also understand that all photographs submitted in connection with this report will become the property of RI and will not be returned.  I warrant that I own all rights in the photographs, including copyright, and hereby grant RI and TRF a royalty free irrevocable license to use the photographs now or at any time in the future, throughout the world in any manner it so chooses and in any medium now known or later developed. This includes the right to modify the photograph(s) as necessary in RI’s sole discretion. This also includes, without limitation, use on or in the web sites, magazines, brochures, pamphlets, exhibitions and any other promotional materials of RI and TRF.

| Print Name: |  | Signature: |  |  | Date: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rotary Title: |  | Club: |  |  |  | District: |  |  |

In our effort to improve our grant program, we’d appreciate your feedback on the following questions:

###### A.  Rotary Impact – select all that apply

|  | Our club or district’s international Rotary connections are stronger as a result of this project. |
| --- | --- |
|  | Club membership has increased as a result of this project. |
|  | Visibility of Rotary in our community has increased. |
|  | Our club’s awareness of the needs in our community has increased. |
|  | Volunteer activity in our club or district has expanded. |
|  | Our club or district is more active in pursuing Foundation grants and Rotary programs. |
|  | Awareness of the needs in our community has increased among Rotarians in other countries. |
|  | Participation in this Matching Grant has not changed our club or district in any significant way. |

B.  Project Sustainability – select all that apply

|  | The project will continue to function without Foundation funds. |
| --- | --- |
|  | Equipment purchased with grant funds is being maintained with local materials and expertise. |
|  | If training was a component of the project, trainees are using their knowledge and skills. |
|  | This project has provided community members with the skills, knowledge, or institutions that will allow them to help themselves. |
|  | The community has initiated additional projects related to the same or similar problems. |
|  | The project has not been sustainable. |

C.  Suggestions

Given your experience, do you have suggestions to improve the Matching Grants program?

If your project clearly demonstrates Rotarian involvement and is worthy of publication, please complete an RI Newstip Form, available on the RI website at www.rotary.org. Please attach action photos showing the beneficiaries or showing active Rotarian involvement and indicate the name of the photographer.

Report Checklist

Does your report include the following?

|  | Time period of reporting |
| --- | --- |
|  | How and what the project accomplished |
|  | Rotarian participation, oversight and management |
|  | Rotary impact |
|  | Itemized report of income and expenses |
|  | A bank statement |
|  | Certifying signature |
|  | Independent Financial Review for grant awards of US$25,001 or more |

Have you done the following?

|  | Made copies of the report for both the host and international partner |
| --- | --- |
|  | Returned surplus funds over US$200 (except in India where all unutilized funds must be returned) |
|  | Made a file to store the report and receipt copies for five years or longer if required by local law |